## Sheet1
No | Criteria | Progress | Estimated Time (h) | Actual Spent Time (h) | Feature Request | Feature Spec
1 | Completion |  | 3 |  | Create function that creates an account | Account should include at least: Name, Email Address, Secure password (with character and length requirement) OPTIONAL public biographical info such as employer, job title, birthday, etc)
2 | Completion |  | 3 |  | Create function that creates an event | Minimum requirement is name of the event, type of the event (birthday, party, conference talk, wedding, etc), event host (name, company), event start date and time, event end date and time, guest list, location, optional message to the guests with additional information about the event, what to bring and prepare, dress code...
3 | Completion |  | 3 |  | Create function that display event | Display events created
4 | Completion |  | 2 |  | Cannot submit form with invalid information | Password validation, name min 2char, email address validation, birthday min.age?, event end later than event start, guest list if account exist?
5 | Completion |  | 1 |  | Validation occurs no later than immediately after user focus leaves the input and is obvious
6 | Delivery | Completed | 2 | 6 | Includes a build process. Assets are minimized and concatenated as appropriate | Update and upgrade if needed node.js and npm ; Set up gulpfile.js ; Set up package.json; Install required node modules ; Try Yeoman generator-webapp out; bower install font-awesome --save and include to head
7 | Form Design |  | 2 |  | Most form prompts (incl. labels, placeholders) phrased friendly, human language | Ask around to test your app
8 | Form Design |  |  |  | There are as few inputs as possible
9 | Input Design |  | 1 |  | Users can pre-fill inputs with existing data | Use autocomplete function
10 | Input Design |  | 1 |  | All inputs have appropriate types
11 | Input Design |  | 1 |  | All inputs are labeled for screen readers
12 | Input Design |  | 1 |  | The autofocus attr is applied to the first input above-the-fold
13 | Input Design |  | 1 |  | The required attr is applied only to vital elements | see min data set
14 | Responsiveness |  | 4 |  | On mobile and desktop with responsive design
15 | UX |  | 2 |  | On mobile is fully functional and reacts to touches naturally
16 | UX |  | 1 |  | Is understandable while using a screen reader | All inputs are labeled for screen readers
17 | UX |  |  |  | Prompts appear in a logical order
TOTAL |  |  | 28 | 6
10.5
Note on E7: Pianovszky Eniko: Update and install npm and node.js took few hours to figure out why windows throws error on some node module install (--no-optional). Figure out windows powershell cmdlets to cd with spaces in the filename use "" , so far I have always used cmdprompts but the npm upgrade-windows required windows powershell. The template gulpfile ran to error which had the exact same features than Yeoman. Time to try it out. Bower install was not automatic due to windows conflicts (again --no-optional), play around with options at install, change folderstructure name and ready to go